## Sprint 1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
| Design GUI | 10 | 0 | 0 | 0 | 0
Create/Edit Characters | Create Character | 5 | 5 | 3 | 0 | 0
Create/Edit Characters | Create Inventory | 5 | 5 | 0 | 0 | 0
Create/Edit Characters | Create Items | 3 | 3 | 0 | 0 | 0
Create/Edit Characters | Create Species/Race | 2 | 2 | 1 | 0 | 0
Create Account | Create Account Creation (User, Player, Dungeon Master) | 7 | 7 | 5
Logging in | Create ViewModel | 10 | 10 | 10
Create Characters | Create Roles | 3 | 2 | 0.5
Connect Online | Json Reading | 3 | 3
Connect Online | Json Writing | 4 | 4
Create/Edit Characters | Create Attributes | 1 | 0
Create Campaign | Create Campaign | 3 | 3 | 1 | 0.5 | 0
Delete Campaign | Delete Campaign | 1 | 1 | 1 | 0 | 0
| Estimate Totals | 57 | 45 | 21.5 | 0.5 | 0

## Sprint 2
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Logout | Implement Logout - Liam | 2 | 0 | 0 | 0 | 0
UI | Correct UI Issues - Shawn | 2 | 2 | 0 | 0 | 0
Campaign Creation | Implement Resources in Campaign- Kelis | 3 | 2 | 1 | 0 | 0
Campaign Creation | Campaign Invite - Kelis,El | 5 | 3 | 2 | 1 | 0
View Character | Create Character Sheet - Shawn | 8 | 8 | 6 | 2 | 0
Create Character | Fix Create Character Issues - Shawn | 10 | 6 | 3 | 0 | 0
Server setup | Implement Character-Server Communication - Shawn | 3 | 3 | 3 | 3 | 0
Server setup | Implement Campaign-Server Communication - kelis | 15 | 13 | 10 | 5 | 0
Server setup | Implement Account-Server Communication -El | 8 | 6 | 3 | 1 | 0
Server setup | Implement Campaign-Invite-Server Communication Kelis,Liam | 10 | 10 | 10 | 1 | 0
| Estimate Totals | 66 | 53 | 38 | 13 | 0

## Sprint 3
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Server Setup | Add a time out to client socket-El | 1 | 0.5 | 0 | 0 | N/A
Edit Character | Fix Character Edit Window Loading -Shawn | 1 | 0 | 0 | 0 | N/A
UI | Convert Context Menu Items to buttons - Shawn, Kelis | 1 | 0 | 0 | 0 | N/A
Character Notes | Add Character Notes- Shawn | 1 | 1 | 0 | 0 | N/A
Campaign Notes | Add Individual Player and Group Notes for a campaign - Kelis | 10 | 3 | 0 | 0 | N/A
System | Implement Missing Tests for Coverage - Liam | 20 | 15 | 10 | 10 | N/A
Character Creation | Implement Support for Skills - Liam | 10 | 10 | 10 | 10 | N/A
Manage/Upload Resource | Add Support For Sharing Resources and Having Multiple Resources Per Capaign - El | 8 | 3 | 1 | 0 | N/A
| Estimate Totals | 52 | 32.5 | 21 | 20 | 0